## Agile Project Plan
Sprint 1 Template Admin
| PROJECT NAME | Member 1 | Member 2 | Start Date | End Date | OVERALL PROGRESS
| Python Flask | Ng. Hoàng Phúc | Ng. Hoàng Minh Phúc | 23/07/2020 | 26/07/2020 | 100%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | DESCRIPTION
| Tìm template Admin | Tìm kiếm giao diện cho trang quản lý | Member 2 | x | 2020-07-23 | 2020-07-23 | 0 | Complete | Tìm được giao diện từ W3Layout
| Xây dựng Project Python Flask | Khởi tạo | Member 1 | x | 2020-07-23 | 2020-07-24 | 1 | Complete | Tạo được project Python Flask gồm đầy đủ các thành phần
| Xây dựng giao diện Admin từ template đã tìm được | Tạo trang Admin | Member 1 + 2 | x | 2020-07-24 | 2020-07-25 | 1 | Complete | Từ template có sẵn, thêm vào project và tách các thành phần dùng Template Inheritance (Block)
| Clone Project on Github | Git Push Origin | Member 1 | x | 2020-07-26 | 2020-07-26 | 0 | Complete | Successfully